STARTUP CONNECT AI

6-Week Sprint Plan

Solo-founder build plan — Lovable → Claude Code handoff, covering all 10 MUST user stories (M1–M10) for v1 launch.

Prepared for Durgesh · B.E. IT, SPPU (2027 batch) · Final Year Project + Startup Build

# How This Plan Works

This compresses the original 10 MUST stories (M1–M10) into 6 weeks instead of 12. That means larger daily scope and less buffer — expect to move fast and cut corners on polish, not on core function. The 9 SHOULD stories (S1–S9) are explicitly deferred to a v1.1 phase after this 6-week window.

- Each week has a single milestone theme and a Friday demo checkpoint — something clickable, even if rough.

- Weeks 1–2: Lovable does the heavy lifting for scaffolding and UI wiring.

- Weeks 3–6: Claude Code takes over once Lovable's complexity ceiling is hit (expected around M5–M7, per your toolchain notes).

- If a week's scope slips, protect the MUST story completion over polish — ship functionally correct, then refine.

Reference documents to have open while executing: PRD (user stories M1–M10 with acceptance criteria + API contracts), UI Design Brief (Stitch prompts per screen), Technical Architecture (data model, endpoints, deployment).

# At a Glance

| Week | Theme | Stories Targeted | Tool | Demo Checkpoint |
| --- | --- | --- | --- | --- |
| 1 | Foundation & Auth | M1 (Onboarding + Auto-Builder) | Lovable + Stitch | Sign up → AI-prefilled profile |
| 2 | Core Profile & Matching Engine v1 | M2, M3 (Profile mgmt, Match generation) | Lovable | See a real match list |
| 3 | Matching Depth + Explainability | M4, M5 (Match detail, Explainable AI) | Lovable → Claude Code handoff | Click a match, see why it matched |
| 4 | Messaging & Intro Flow | M6, M7 (Intro requests, Messaging) | Claude Code | Founder ↔ Investor can message |
| 5 | Meetings, Search & Notifications | M8, M9 (Scheduler, RAG search) | Claude Code | Book a meeting end-to-end |
| 6 | Hardening, Analytics & Launch Prep | M10 (final MUST) + QA + deploy | Claude Code | Full MUST-path demo, deployed |

WEEK 1 — Foundation, Auth & AI Onboarding

Goal: a user can sign up, choose a role, and get an AI-prefilled profile from a pitch deck + LinkedIn URL. This is M1 — the highest-leverage story since every later feature depends on profile data existing.

## Day-by-day

- Day 1–2: Repo setup, Supabase schema (users, profiles tables from Technical Architecture data model), Clerk auth wired, Vercel + Railway environments live.

- Day 3–4: Lovable scaffold using Stitch screens S-01 (Landing), sign-up, role selection, Onboarding Step 1 (deck upload + LinkedIn URL).

- Day 5: Wire PDF parsing + LLM extraction (Groq) for the Auto-Builder, confidence-score highlighting on low-confidence fields per M1 acceptance criteria.

- Day 6: Onboarding Step 2 prefilled review screen, edit + save flow, error states (invalid LinkedIn URL, failed upload, LLM failure).

- Day 7: Buffer + demo prep. Test full path: sign up → upload deck → prefilled profile → save.

## Definition of done

- M1 acceptance criteria pass end-to-end (see PRD).

- Supabase profiles table populated correctly from a real test deck.

- Auth flow (Clerk) working for founder + investor + mentor roles.

WEEK 2 — Core Profile & Matching Engine v1

Goal: profile management is complete and the hybrid matching engine returns a real, ranked match list. This is M2 + M3 — the platform's core value proposition becomes visible for the first time.

## Day-by-day

- Day 1–2: Profile view/edit screens (S-09 dashboard, profile settings), L2 auto-aggregated signals wiring (momentum signals from Business Architecture's 3-layer model).

- Day 3: Embedding pipeline — sentence-transformers/all-MiniLM-L6-v2 for text profiles, CLIP ViT-B/32 if media present. Store vectors in Qdrant Cloud.

- Day 4–5: Hybrid matching logic — cosine similarity (content) + collaborative signal, blended per the worked example in your deck (0.84 / 0.69 → 0.78 hybrid score). Target the 400ms P95 latency budget from Technical Architecture.

- Day 6: Match List screen (S-13) — highest-iteration screen per UI brief. Ranked cards, basic filters.

- Day 7: Buffer + demo prep. Seed 20–30 realistic test profiles (investors + founders) so matches look real, not empty-state.

## Definition of done

- M2 (profile management) and M3 (match generation) acceptance criteria pass.

- Match List returns ranked, non-trivial results against seeded data.

- Matching latency measured and logged (even if not yet at 400ms target).

WEEK 3 — Match Detail, Explainability & Tool Handoff

Goal: match detail screen with explainable AI reasoning (M4, M5). This week is also the expected Lovable → Claude Code handoff point — plan for a half-day of repo re-orientation.

## Day-by-day

- Day 1: Assess Lovable ceiling. If hit, commit to GitHub, open in Claude Code: "Read the PRD. We've built M1–M3. Next story is M4. Here's the full card: [paste]."

- Day 2–3: Match Detail screen (S-14ish) — full profile view, match score breakdown.

- Day 4–5: Explainable AI (M5) — surface why-matched reasoning (which signals drove the score: sector fit, stage fit, thesis overlap). This is a core differentiator per your research report — don't cut it.

- Day 6: Edge cases — no matches found, stale profile data, mismatched stage warnings.

- Day 7: Buffer + demo prep.

## Definition of done

- M4 and M5 acceptance criteria pass.

- Every match shown includes a human-readable explanation, not just a score.

- Claude Code has full repo context and can pick up stories independently.

WEEK 4 — Intro Requests & Messaging

Goal: founder and investor can request an intro and message each other (M6, M7). This is the first two-sided interaction loop — treat it as the riskiest week technically (real-time messaging + notification plumbing).

## Day-by-day

- Day 1–2: Intro request flow (M6) — request, accept/decline states, notification on both sides.

- Day 3–5: Messaging (M7) — thread UI, Supabase realtime or polling fallback, read receipts if in scope, basic rate-limiting/abuse guard.

- Day 6: Notification system — in-app + email (transactional) for intro accepted, new message.

- Day 7: Buffer + demo prep. Test two-account flow live (founder account + investor account messaging each other).

## Definition of done

- M6 and M7 acceptance criteria pass.

- A full two-sided conversation can happen without page reload issues or lost messages.

WEEK 5 — Meeting Scheduler & RAG Search

Goal: meeting booking end-to-end and RAG-powered search across profiles (M8, M9). These are more self-contained than Week 4's messaging, so this week should feel comparatively lighter — use slack days for anything that slipped.

## Day-by-day

- Day 1–2: Meeting scheduler (M8) — availability, booking, calendar confirmation, cancel/reschedule.

- Day 3–4: RAG search (M9) — Qdrant-backed semantic search across founder/investor profiles with Groq for query understanding + result summarization.

- Day 5: Catch-up slot — absorb anything unfinished from Weeks 1–4.

- Day 6: Analytics events wired (PostHog/Mixpanel) per the Analytics Event Dictionary in the PRD.

- Day 7: Buffer + demo prep.

## Definition of done

- M8 and M9 acceptance criteria pass.

- Search returns relevant results for a natural-language query, not just keyword match.

- Core analytics events firing correctly (signup, match viewed, intro sent, message sent, meeting booked).

WEEK 6 — Final MUST Story, Hardening & Launch Prep

Goal: ship M10, then spend the back half of the week on QA, security basics, and deployment — not new features. This week protects launch quality over scope.

## Day-by-day

- Day 1–2: M10 (final MUST story — settings/account management per PRD) implementation.

- Day 3: Security pass — v1 minimum requirements from Technical Architecture (auth checks on all endpoints, rate limiting, input validation, RLS policies on Supabase tables).

- Day 4: Full regression walk of all 10 MUST stories against their acceptance criteria — use the PRD's Definition of Done checklist per story.

- Day 5: Mobile responsiveness pass (per Global UX Standards) and empty/error states audit across all screens.

- Day 6: Production deploy — Vercel + Railway prod environments, environment variables locked, cost check against the ₹160–180/month projection.

- Day 7: Final demo — full MUST-path walkthrough, deployed and live.

## Definition of done — v1 launch

- All 10 MUST stories (M1–M10) pass acceptance criteria.

- App is deployed to production and reachable by a real URL.

- No known critical bugs on the core path: sign up → profile → match → intro → message → meeting.

- SHOULD stories (S1–S9) formally deferred to v1.1 — write them down so they don't get lost, don't build them yet.

# Risk Notes — Where 6 Weeks Is Tight

Compressing from 12 weeks to 6 roughly doubles daily scope. Two spots are most likely to slip:

- Week 2 (matching engine): embeddings + hybrid scoring + Qdrant integration is genuinely the hardest technical piece. If it slips, let it eat into Week 3's buffer day rather than cutting explainability (M5) — explainability is a stated differentiator in your research report.

- Week 4 (messaging): real-time features are notoriously slippery. A polling-based "good enough" implementation is fine for v1 — don't over-invest in true real-time (websockets) if time is short; that's a good v1.1 upgrade.

If you fall more than 2 days behind at any weekly checkpoint, the recommended cut is: drop RAG search (M9) sophistication to basic keyword/filter search for launch, and revisit semantic search in v1.1. Do not cut M1–M5 (onboarding through explainability) — that's the core demo.